## Project
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | Sign Up | Signup | User, Enterprise | Register a user/enterprise account | Anh Quang | Done | iter1 | none
2 | Login | Manual Login | User, Enterprise, Admin | Log in to the system | Anh Quang | Done | iter1 | none
3 | Login | Login with Google | User | Log in to the system using your Google account | Thế Anh | Done | iter1 | none
4 | Logout | Logout | User, Enterprise, Admin | Log out of the system | Ngọc Ánh | Done | iter1 | none
5 | Forgot Password | Forgot Password | User, Enterprise | Reset fogotten password | Thế Anh | Done | iter1 | none
6 | Change Password | Change Password | User, Enterprise | Change account password | Anh Quang | Done | iter1 | none
7 | View User Profile | View User Profile | User | View user profile | Ngọc Ánh | Done | iter1 | none
8 | Update User Profile | Update User Profile | User | Update user profile | Ngọc Ánh | Done | iter1 | none
9 | View Enterprise Profile | View Enterprise Profile | Enterprise | View enterprise profile | Anh Quang | Done | iter1 | none
10 | Update Enterprise Profile | Update Enterprise Profile | Enterprise | Update enterprise profile | Anh Quang | Done | iter1 | none
11 | Search Job | Search Job | Guest,User, Enterprise | Search a job | Ngọc Ánh | Done | iter1 | none
12 | View Job Detail | View Job Detail | Guest,User, Enterprise, Admin | View detailed job information | Anh Quang | Done | iter1 | none
13 | View CV | View CV | User, Enterprise | View details of user's CV | Thế Anh | Doing | iter2 | none
14 | Write CV | Write CV | User | Write a new CV | Anh Tú | Done | iter2 | none
15 | Upload CV | Upload CV | User | Update a CV to a job post | Thế Anh | Done | iter2 | none
16 | Create Comment | Create Comment | User, Enterprise | Create Comment on a job post | Đình Vũ | Doing | iter2
17 | View Comment | View Comment | User, Enterprise | See posted comments | Đình Vũ | Doing | iter2
18 | Edit Comment | Edit Comment | User, Enterprise | Edit posted comments | Đình Vũ | Doing | iter2
19 | Delete Comment | Delete Comment | User, Enterprise | Delete posted comments | Đình Vũ | Doing | iter2
20 | Send Report | Send Report | User, Enterprise | Send report an post job | Đình Vũ | Doing | iter3
21 | Chat | Chat | Guest, User, Enterprise, Admin | Chat for support when needed | Anh Tú | Done | iter3
22 | Online Interview | Interview | User, Enterprise | Users and enterprises can interview online | Anh Tú | Done | iter3
23 | Delete Account | Delete Account | Admin | Delete an already created account | Anh Tú | Doing | iter3
24 | Lock Account | Lock Account | Admin | Lock an already created account | Anh Tú | Doing | iter3
25 | Unlock Account | Unlock Account | Admin | Unlock a locked account | Anh Tú | Doing | iter3
26 | Accept Job | Accept Job | Admin | Accept posting a new job post | Anh Quang | Done | iter4 | none
27 | Reject Job | Reject Job | Admin | Reject posting a new job post | Anh Quang | Done | iter4
28 | Delete Job | Delete Job | Enterprise | Delete a posted job post | Anh Quang | Done | iter4
29 | Statistic | Statistic | Admin | Statistics on the number of existing accounts and job posts | Ngọc Ánh | Done | iter4
30 | Write Job | Write Job | Enterprise | Write a new Job post | Anh Quang | Done | iter4
31 | Post Job | Post Job | Enterprise | Post a new job post on the homepage | Anh Quang | Done | iter4
32 | Accept CV | Accept CV | Enterprise | Accept user's application CV | Thế Anh | Done | iter4
33 | Reject CV | Reject CV | Enterprise | Reject user's application CV | Thế Anh | Done | iter4

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Sign Up | Signup | Register a user/enterprise account | Anh Quang | Done | Done | Done
2 | Login | Manual Login | Log in to the system | Anh Quang | Done | Done | Done
3 | Login | Login with Google | Log in to the system using your Google account | Thế Anh | Done | Done | Done
4 | Logout | Logout | Log out of the system | Ngọc Ánh | Done | Done | Done
5 | Forgot Password | Forgot Password | Reset fogotten password | Thế Anh | Done | Done | Done
6 | Change Password | Change Password | Change account password | Anh Quang | Done | Done | Done
7 | View User Profile | View User Profile | View user profile | Ngọc Ánh | Done | Done | Done
8 | Update User Profile | Update User Profile | Update user profile | Ngọc Ánh | Done | Done | Done
9 | View Enterprise Profile | View Enterprise Profile | View enterprise profile | Anh Quang | Done | Done | Done
10 | Update Enterprise Profile | Update Enterprise Profile | Update enterprise profile | Anh Quang | Done | Done | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Search Job | Search Job | Search a job | Ngọc Ánh | Done | Done | Done
2 | View Job Detail | View Job Detail | View detailed job information | Anh Quang | Done | Done | Done
3 | View CV | View CV | View details of user's CV | Thế Anh | Doing | Done | Done
4 | Write CV | Write CV | Write a new CV | Anh Tú | Done | Done | Done
5 | Upload CV | Upload CV | Update a CV to a job post | Thế Anh | Done | Done | Done
6 | Create Comment | Create Comment | Create Comment on a job post | Đình Vũ | Doing | Done | Done
7 | View Comment | View Comment | See posted comments | Đình Vũ | Doing | Done | Done
8 | Edit Comment | Edit Comment | Edit posted comments | Đình Vũ | Doing | Done | Done
9 | Delete Comment | Delete Comment | Delete posted comments | Đình Vũ | Doing | Done | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Delete Comment | Delete Comment | Delete posted comments | Đình Vũ | Doing | Done | Done
2 | Send Report | Send Report | Send report an post job | Đình Vũ | Doing | Done | Done
3 | Chat | Chat | Chat for support when needed | Anh Tú | Done | Done | Done
5 | Online Interview | Interview | Users and enterprises can interview online | Anh Tú | Done | Done | Done
6 | Delete Account | Delete Account | Delete an already created account | Anh Tú | Doing | Done | Done
7 | Lock Account | Lock Account | Lock an already created account | Anh Tú | Doing | Done | Done
8 | Unlock Account | Unlock Account | Unlock a locked account | Anh Tú | Doing | Done | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Accept Job | Accept Job | Accept posting a new job post | Anh Quang | Done | Done | Done
2 | Reject Job | Reject Job | Reject posting a new job post | Anh Quang | Done | Done | Done
3 | Delete Job | Delete Job | Delete a posted job post | Anh Quang | Done | Done | Done
4 | Statistic | Statistic | Statistics on the number of existing accounts and job posts | Ngọc Ánh | Done | Done | Done
5 | Write Job | Write Job | Write a new Job post | Anh Quang | Done | Done | Done
6 | Post Job | Post Job | Post a new job post on the homepage | Anh Quang | Done | Done | Done
7 | Accept CV | Accept CV | Accept user's application CV | Thế Anh | Done | Done | Done
8 | Reject CV | Reject CV | Reject user's application CV | Thế Anh | Done | Done | Done
Note on G2: KienNT: The name of section in the SRS (software requirement specification) document
Note on H2: KienNT: The name of section in the SDS (software design specification) document